## Backlog
Task | What to do | Priority | Effort | Status | Comment
APK Version on top of screen | Under Name or around Wartsila Logo, add global constant | High | Low | Completed |  | Very High | Low | Investigate
APK Version on SyncMobileData | Create SFDC field, after it is on Production | High | Medium | Completed |  | High | Medium | Not Started
APK Version on SyncMobileData | Mobile app uploads it's own APK version | High | Medium | Completed |  | Medium | Longer | In Progress
Error Text field on SyncMobileData | Create SFDC long text area field, move it to Production | Very High | Low | Completed | include in change set | Low | Hardcore | Not Now
Apex Classes save Error Logs | Each Apex class and Catch block, pass SMD record through functions or return String | High | Longer | Not Started | add as Improvement Task | Nice to Have |  | Completed
Feed/Post to store Created.Name | Feed/Post stores/uses Created.Name on new records, remove Left Join on User | Low | Medium | Not Started
Remove Fetch_Count jobs | and unused/unnecessary functions, test Sync and first load of App | Low | Medium | Not Started
Fix 'NaN = undefined' | and test if nothing is broken, first fix usage occurances, then Constants.js | Low | Low | In Progress
% Progress Bar on Syncing | Progress based on actual number of job against total jobs in MainJob | Nice to Have | Hardcore | Not Now
Advanced Alerts in Mobile | For each Object/Case to have a bit different error message | Very High | Longer | In Progress | add as Improvement Task
Disable Multiple Synchronizations | Synchronize button, track ongoing push/fetch. Reset on complete plus test with errors | Medium | Medium | Completed
Improve Page Layouts | on DEV/TEST, to make easier work with FSM Objects | Nice to Have | Medium | Not Now
Database clean up | remove unused Queries | Medium | Medium | Not Started
ErrorHandler class | create js that will handle errors and store them | Very High | Medium | Completed